## Overview
Test cases for 10-prospecting.html (Lead discovery and research)
Test data: Lead_Research_Sample_Dataset.xlsx (7,498 lead rows, answer key in its Row key and Account key sheets). First run: 3 Oct 2026, headless Chromium, with the Excel library served locally. Timings depend on the machine; treat them as relative.
Test type | What it covers | Tooling | When to run | Cases | Pass | Fail | Gap | Not run
Unit | Tests one function at a time, with no browser: the rules engine (demandai-engine.js) and the page's pure helpers. | node --test (already in package.json); table-driven cases; the dataset's Row key as the oracle | Every commit
Component | Tests one piece of the page (upload, checks pop-up, tables, filters, selection, save, saved lists, roles) in a real browser, with controlled input. | Playwright with routes that serve the Excel library locally and block fonts | Every pull request
Smoke | A short, fast run over the critical path to decide whether a build is worth testing further. Stop at the first failure. | Playwright, one spec, under 2 minutes | Every deploy
User acceptance | Business scenarios from the Lead discovery and research flow (3.1–3.6), run by sales ops or the client with the generated dataset and its answer key. | Manual, with the Row key and Account key sheets as the expected results; timed where performance matters | Before each client milestone
Total
Status key
Pass | Behaved as expected
Fail | A defect: the page or rule does not do what it is meant to
Gap | Works as coded, but misses a business need from the PDF flow or the dataset
Not run | Written, not yet executed
What the first run tells us
Inference | Evidence and recommendation | Test cases
Engine is fast; the page is the bottleneck | The rules engine processes 7,498 rows in 0.18 s and 75k rows in 1.2 s. The page takes 7.3 s to show the list and builds 275,831 DOM nodes, and every keystroke in search re-renders all rows (2.5 s of script). Paginate or virtualise the tables and debounce search before the client's real file arrives.
The full list cannot be saved or sent to Scoring | A screened list from this file is 8.1 MB; browser storage holds about 5 MB, so Save fails and the message wrongly blames browser settings. Any file over about 4,000 rows will hit this. Store lists in IndexedDB or on the server, and say clearly when a list is too large.
Validation rules miss real-world mess | Malformed-looking emails (double dots, trailing dot, mailto:), webmail and role mailboxes pass; country codes and spelling variants knock in-region accounts out; alias-email duplicates and company-name variants slip through. The dataset's Row key lists every affected row, so each fix can be checked by re-running the same file.
Persona and classification rules are too narrow | 41% of contacts get no persona because "Instrument Engineer" doesn't match "instrumentation"; 59% of accounts need review because unmapped industries fall to "Other". Expect the AI classifier and a wider persona list to carry most of the load.
Parts of the PDF flow are not on this page yet | There is no downloadable validation report for the client (3.2), no D1–D6 codes shown per issue, and no readiness go/no-go (3.3). Owner email doesn't limit what a rep sees.
What works well | Every count on screen matches the engine; all missing-field, malformed-email, exact-duplicate, opt-out and consent cases in the dataset were caught; HTML in the file is escaped; the right sheet is picked from a 9-sheet workbook; and small lists save and reload.
Accessibility needs a pass | The upload can't be reached by keyboard and the tabs and filters are clickable <div>s. Run axe-core in the component suite.

## Unit
Unit tests · Tests one function at a time, with no browser: the rules engine (demandai-engine.js) and the page's pure helpers.
ID | Test case | Function / component under test | Aspect | Preconditions and test data | Steps | Expected result | Priority | How to automate | First run (3 Oct 2026) | Observed
UT-01 | CSV parser handles quotes, embedded commas, escaped quotes, line breaks and a BOM | parseCSV() | Functional | String: BOM + a,"b,c","d ""q""" CRLF 1,"x\ny",3 | Call DemandAI.parseCSV(text) | Two rows; "b,c" kept as one cell; d "q" unescaped; the line break stays inside the cell; BOM stripped | High | node:test, no browser | Pass | Parsed exactly as expected
UT-02 | CSV writer round-trips through the parser | toCSV() + parseCSV() | Functional | Cells with a comma, a quote and a line break | parseCSV(toCSV(rows)) | Output equals input | Medium | node:test, property-based (fast-check) for random strings | Pass | Round-trip identical
UT-03 | Header row is found under the title row, and the format-hint row is skipped | readTable() | Functional | Grid: title row, header row, "Text*" hint row, 1 data row | processLeads(grid) | rowsRead = 1; the hint row is reported as info, not loaded as a contact | High | node:test | Pass | rowsRead = 1
UT-04 | Header names are matched regardless of case, spaces, stars and hyphens | normHeader() | Functional | Headers written " FIRST NAME* ", "Company-Name" | processLeads(grid) | All columns recognised; no "missing column" issue | High | node:test, table-driven | Pass | Contact loaded, no column issues
UT-05 | A missing required column is reported once, against the header row | readTable() | Functional | Template without owner_email | processLeads(grid) | Issue "Required column "owner_email" is missing" (flag); rows still processed | High | node:test | Pass | Issue raised as expected
UT-06 | A file without the anchor column (company_name) stops processing | readTable() | Functional | Grid [["a","b"],["1","2"]] | processLeads(grid) | One stop issue: header row not found; no contacts | High | node:test | Pass | Single stop issue
UT-07 | Extra columns are ignored and reported as info | readTable() | Functional | Template + "notes" column | processLeads(grid) | "Column "notes" isn't in the template", severity info | Low | node:test | Pass | Info issue raised
UT-08 | Y/N parsing accepts Y, N, Yes, No in any case and with spaces; rejects TRUE, 1, X | yesNo() | Functional | opt_out = Yes, n, TRUE, blank, " y " | processLeads per value; read optOutUnknown | Yes/n/" y " accepted; TRUE and blank make the opt-out unknown (not contactable) | High | node:test, table-driven | Pass | [false, false, true, true, false] as expected
UT-09 | Numbers with $, commas or "USD" are read and flagged; text numbers are rejected | parseNumber() | Functional | annual_revenue_usd = "$2,400,000,000" and "2.4B" | processLeads | $2,400,000,000 → 2400000000 with a reformat flag; "2.4B" → "isn't a number", treated as blank | High | node:test | Pass | Both behave as specified
UT-10 | Malformed emails are rejected (no @, two @, no TLD, space, placeholder) | EMAIL_RE | Functional | Lead_Research_Sample_Dataset.xlsx: Row key cases EM-NO-AT, EM-DOUBLE-AT, EM-NO-TLD, EM-SPACE, EM-PLACEHOLDER | processLeads on each value | Each flagged "malformed" (D3); email not used | High | node:test over the Row key rows | Pass | 195 of 195 dataset rows flagged
UT-11 | Emails that pass the regex but are invalid: double dots, trailing dot, mailto:, angle brackets | EMAIL_RE | Functional | a..b@nw..com, a@nw.com., mailto:a@nw.com | processLeads on each value | Each should be flagged malformed | High | node:test | Fail | All three accepted as valid emails (only 48 of 95 dataset rows flagged, and those only for other reasons)
UT-12 | LinkedIn URL must be a profile URL | LINKEDIN_RE | Functional | company page, Sales Navigator URL, search URL, bare text | processLeads on each value | Each flagged "isn't a profile URL"; LinkedIn not used | Medium | node:test | Pass | 70 of 70 dataset rows flagged
UT-13 | Duplicate by email is case- and space-insensitive | processLeads() dedupe | Functional | Same email, second row in upper case | processLeads | Second row merged (D5) into the first | High | node:test | Pass | merged = 1; 80 of 80 dataset rows
UT-14 | Duplicate by LinkedIn ignores http/https, www, trailing slash and query string | normLinkedIn() | Functional | https://www.linkedin.com/in/aditi vs http://linkedin.com/in/aditi/ | processLeads | Merged (D5) | High | node:test | Pass | merged = 1
UT-15 | Duplicate by LinkedIn on a country subdomain (sg.linkedin.com) | normLinkedIn() | Functional | www.linkedin.com/in/aditi vs sg.linkedin.com/in/aditi | processLeads | Merged (D5) | Medium | node:test | Fail | Not merged: counted as two people (11 of 70 dataset LinkedIn duplicates missed)
UT-16 | A merged duplicate fills blanks on the first row | processLeads() merge | Functional | Row 1 seniority blank, repeat has "Director" | processLeads | Contact seniority = Director | Medium | node:test | Pass | Blank filled from the repeat
UT-17 | Same person with a different email alias and no LinkedIn | processLeads() dedupe | Functional | aditi.rao@ and a.rao@, same name and company | processLeads | Flagged as a possible duplicate | Medium | node:test | Gap | Not detected: exact-key matching only (3 of 70 dataset rows caught)
UT-18 | A row without company_name is not loaded | processLeads() | Functional | company_name blank | processLeads | notLoaded = 1, severity stop, no account created | High | node:test | Pass | 45 of 45 dataset rows not loaded
UT-19 | Domain must be a bare domain | processLeads() domain check | Functional | company_domain = https://www.nw.com/ | processLeads | "isn't in the form company.com"; domain not used for matching | Medium | node:test | Pass | Flagged
UT-20 | Persona matching on job title | personaOf() | Functional | Head of Instrumentation, Senior Instrument Engineer, Process Control Engineer, Plant Manager, Project Manager, Kepala Instrumentasi | personaOf(title) for each | Instrumentation and control roles are Primary; operations roles Secondary | High | node:test, table-driven over a title list agreed with sales | Gap | "Senior Instrument Engineer" and "Process Control Engineer" come back None; 41% of dataset contacts get no persona
UT-21 | Vertical classification and confidence | classify() | Functional | Industry only: Oil & Gas - Refining, Petrochemicals, LNG, Downstream Oil & Gas, blank | classify(industry, "") | Refining/Petrochemicals/Gas processing at medium; unmapped → Other, low, needs review | High | node:test | Pass | As expected; "Downstream Oil & Gas" falls to Other (an AI classifier would decide)
UT-22 | Classification is high confidence when industry and site process agree | classify() | Functional | industry Refining, site Crude refining | classify() | confidence high | Medium | node:test | Pass | Covered by the existing golden test
UT-23 | Pilot-region knock-out ignores case | buildAccounts() region rule | Functional | country = singapore | processLeads | Account passes | High | node:test | Pass | Passes
UT-24 | Pilot-region knock-out accepts common variants (SG, Viet Nam, Việt Nam, Phillipines) | buildAccounts() region rule | Functional | Lead_Research_Sample_Dataset.xlsx: accounts tagged FMT-COUNTRY in Account key | processLeads | Accounts in the pilot region pass | High | node:test | Fail | All variants excluded as "outside the pilot region": about 50 in-region dataset accounts lost
UT-25 | Managed-separately and all-opted-out knock-outs | buildAccounts() | Functional | managed_separately = Y; every contact opt_out = Y | processLeads | Excluded with the matching reason | High | node:test | Pass | Both reasons as specified
UT-26 | Contactability matrix: channel × consent × opt-out | processLeads() reachability | Functional | Verified email + LinkedIn; unverified email + LinkedIn; unverified email only; nothing; consent Implied; opt-out blank | processLeads per case | reachableBy = email and LinkedIn / LinkedIn / none / none; Implied or blank opt-out → not contactable | High | node:test, table-driven | Pass | All combinations as specified
UT-27 | Company details that differ between rows are flagged | buildAccounts() consistency | Functional | Two rows, same company, different revenue | processLeads | One "Differs from row N" issue; first row's value used | Medium | node:test | Pass | 58 of 60 dataset rows flagged; 2 not flagged, to investigate
UT-28 | Counts add up | processLeads() stats | Functional | Lead_Research_Sample_Dataset.xlsx Lead template (7,498 rows) | processLeads | rowsRead = notLoaded + merged + contacts | High | node:test | Pass | 7,498 = 45 + 457 + 6,996
UT-29 | Same file gives the same result every time | processLeads() | Non-functional · reliability | Lead_Research_Sample_Dataset.xlsx | Run twice, compare stats | Identical | Medium | node:test | Pass | Identical
UT-30 | Engine throughput at 1× and 10× the dataset | processLeads() | Non-functional · performance | Lead_Research_Sample_Dataset.xlsx, then 75k rows (10 copies) | Time processLeads | Under 1 s for 7.5k rows; scales roughly linearly | Medium | node:test with a time budget | Pass | 0.18 s for 7,498 rows; 1.2 s for 74,983 rows
UT-31 | Page helpers: HTML escaping, initials, avatar colour | esc(), initials(), avColor() in the page | Functional | esc('<img onerror>'), initials("Wei Ming Tan"), avColor same id twice | Extract the helpers to a module, or evaluate in jsdom | Escaped; "WM"; same colour each time | Medium | jsdom or Playwright page.evaluate | Not run | esc() confirmed indirectly by CT-30
UT-32 | Issue → check mapping covers every issue text the engine can produce | checkOf() in the page | Functional | Every issue in the dataset run | Group issues with checkOf; list the issue texts that fall into "required" by default | Only missing-field issues land in "Required fields" | Medium | Playwright page.evaluate | Gap | Fallback bucket: "No owner rep", "isn't an email", "No company size" all land in "Required fields", so the counts mix different problems

## Component
Component tests · Tests one piece of the page (upload, checks pop-up, tables, filters, selection, save, saved lists, roles) in a real browser, with controlled input.
ID | Test case | Function / component under test | Aspect | Preconditions and test data | Steps | Expected result | Priority | How to automate | First run (3 Oct 2026) | Observed
CT-01 | Upload card renders with required fields and pilot region | renderStart("upload") | Functional | Fresh page | Open 10-prospecting.html | Drop zone, "Use sample data", "Download lead template", required-field list and the 6 pilot countries visible | High | Playwright | Pass | All visible; loaded in 162 ms
CT-02 | Choosing a file opens the checks pop-up | Drop zone + #fileInput → onFile() | Functional | Lead_Research_Sample_Dataset.xlsx | setInputFiles(#fileInput) | Checks pop-up appears | High | Playwright setInputFiles | Pass | Pop-up after 1.5 s (read + parse + rules)
CT-03 | Drag and drop a file onto the drop zone | dropZone drop handler | Functional | Lead_Research_Sample_Dataset.xlsx | Dispatch dragover / drop with a DataTransfer | Border highlights on dragover; file processed on drop | Medium | Playwright dispatchEvent with DataTransfer | Not run
CT-04 | Wrong file type is refused with a message | readFileToGrids() | Functional | bad.txt | Upload | Toast "Use a .csv or .xlsx file"; nothing processed | High | Playwright | Pass | Toast shown
CT-05 | Excel library unavailable (CDN blocked) | readFileToGrids() | Non-functional · reliability | Block cdnjs.cloudflare.com | Upload an .xlsx | Toast tells the user to save as CSV | Medium | Playwright route.abort() | Not run
CT-06 | Multi-sheet workbook: the "Lead template" sheet is used, guide and answer-key sheets ignored | pickSheet() | Functional | Lead_Research_Sample_Dataset.xlsx (9 sheets) | Upload | Sheet badge reads "Lead template"; 7,498 rows read | High | Playwright | Pass | 7,498 rows read from "Lead template"
CT-07 | Checks pop-up runs all 12 steps and shows a result for each | openChecks() | Functional | Lead_Research_Sample_Dataset.xlsx | Upload; wait for footer | Each step turns green/amber/red/grey with a count and the first 5 rows; progress bar reaches 100% | High | Playwright | Pass | e.g. Email format 197 found; Duplicates 457; Opt-outs 259; Classification 854 need review; Knock-outs 275 excluded
CT-08 | Checks footer totals match the engine | openChecks() footer | Functional | Lead_Research_Sample_Dataset.xlsx | Read footer text | "7,382 issues · 1,168 of 1,443 accounts pass · 4,933 contacts in the list" | High | Playwright vs node engine run | Pass | Matches the engine exactly
CT-09 | Checks pop-up timing | openChecks() animation | Non-functional · performance / usability | Lead_Research_Sample_Dataset.xlsx | Time from upload to "View the list" | Under 5 s | Low | Playwright timing | Fail | 6.4 s: 1.5 s processing plus a fixed 4.6 s animation (12 × 380 ms), even for tiny files
CT-10 | Stat cards show rows, issues, accounts, excluded and final list | renderRun() stats | Functional | Lead_Research_Sample_Dataset.xlsx | View the list | Rows read 7,498 (45 not loaded · 457 merged); Issues 7,382; Accounts 1,443; Excluded 275; Final list 4,933 of 6,996 | High | Playwright | Pass | All five values correct
CT-11 | Final list table renders every contact with 15 columns | drawListRows() | Functional | Lead_Research_Sample_Dataset.xlsx | View the list; count rows | 6,996 rows; email shows Verified / Not verified / Malformed | High | Playwright | Pass | 6,996 rows rendered
CT-12 | Final list render time and DOM size at 7.5k rows | drawListRows() | Non-functional · performance | Lead_Research_Sample_Dataset.xlsx | Time "View the list" → table visible | Under 2 s; DOM under 50k nodes (virtualised or paginated) | High | Playwright + performance.now | Fail | 7.3 s; 275,831 DOM nodes; no pagination or virtual scrolling
CT-13 | Status filter pills | visibleContacts() filt | Functional | Lead_Research_Sample_Dataset.xlsx | Click All / In the final list / Not contactable / Not in the list | Row counts add up to 6,996; In the final list = 4,933 | High | Playwright | Pass | In the final list = 4,933 rows (0.9 s to redraw)
CT-14 | Search by name, company or title | visibleContacts() q | Functional | Lead_Research_Sample_Dataset.xlsx | Type "refin" | Only matching rows; case-insensitive | High | Playwright | Pass | 877 rows match "refin"
CT-15 | Search responsiveness while typing | toolbar oninput → drawListRows() | Non-functional · performance | Lead_Research_Sample_Dataset.xlsx | Type one character in the search box | Under 200 ms per keystroke (debounced) | High | Playwright + performance.now | Fail | 2.5 s of script on the first keystroke (redraws ~6,900 rows, no debounce); 14 s end to end in headless Chromium
CT-16 | Search with no match shows the empty state | table() empty | Functional | Search "zzzz" | Type | "No contacts match." | Low | Playwright | Pass | Empty state shown
CT-17 | Only contacts in the list can be selected | selectable() | Functional | Lead_Research_Sample_Dataset.xlsx | Look at the checkbox column for excluded / opted-out contacts | Checkbox only on "In the list" and "Not contactable" rows; "—" on others | High | Playwright | Pass | Sample: 14 checkboxes for 14 selectable of 17 contacts
CT-18 | Select all respects the filter and shows a partial state | toggleAll(), updateSelBar() | Functional | Lead_Research_Sample_Dataset.xlsx | Filter "In the final list" → select all; then untick one | All 4,933 selected; header box becomes indeterminate after unticking one | High | Playwright | Pass | 4,933 selected in 1.0 s; button reads "Send 4933 selected to Scoring →"
CT-19 | Selection bar count and Clear | selBar | Functional | Select 3 contacts | Read bar; click Clear | "3 prospects selected"; Clear empties it | Medium | Playwright | Pass | As expected
CT-20 | Accounts tab: columns, money format, classification reason, knock-out reason | drawAccRows() | Functional | Lead_Research_Sample_Dataset.xlsx | Open Accounts | 1,443 rows; revenue as USD 2.4bn / USD 850m; excluded rows show the reason | High | Playwright | Pass | 1,443 rows in 0.46 s
CT-21 | Accounts filters: Pass / Excluded / Needs review | drawAccRows() filt | Functional | Lead_Research_Sample_Dataset.xlsx | Click each pill | Pass 1,168; Excluded 275; Needs review = accounts with no mapping match | High | Playwright | Pass | Needs review = 854 (59% of accounts)
CT-22 | Issue cell shows the first issue, "+N more", and every issue on hover | issueCell() | Functional | Row with 3+ issues | Hover the cell | Dot colour = worst severity; tooltip lists all issues with fixes | Medium | Playwright title attribute | Not run
CT-23 | Duplicate issue appears on the row it was merged into | issuesFor() | Functional | Row key DUP-EXACT pair | Find the original row | Shows "Duplicate of row N" against the kept row | Medium | Playwright | Not run
CT-24 | Issues for rows not loaded are listed above the table | unattachedNotice() | Functional + usability | Lead_Research_Sample_Dataset.xlsx | View the list | Panel lists the rows not loaded | Medium | Playwright | Fail | 289 issues listed one per line in a panel above the table, pushing the list down several screens
CT-25 | Save pop-up: default name, Enter to save, Cancel, click outside to close | openSave(), saveList() | Functional | Sample data | Open Save list; check name; press Enter | Name = file name · date; saved; toast "Saved as …" | High | Playwright | Pass | Works for the sample and for 50 selected rows
CT-26 | Save the full screened list from a 7.5k-row file | saveList() → localStorage | Non-functional · capacity / reliability | Lead_Research_Sample_Dataset.xlsx | View the list → Save list → Save | List saved, or a clear message about the size limit | Critical | Playwright | Fail | Not saved: the list is 8.1 MB, more than the ~5 MB localStorage limit. Message wrongly says "This browser blocks storage… Allow site data"; pop-up stays open
CT-27 | Saved lists tab: list appears with counts, rename, delete | renderStart("saved"), startRename(), removeList() | Functional | One saved list | Open Saved lists; rename (Enter and Escape); delete | Counts shown; rename saved on Enter, cancelled on Escape; delete removes it | High | Playwright | Pass | Saved list shown with counts; rename and delete not run
CT-28 | "Score →" and "Save and go to Scoring" open Scoring with the list id | saveList(true) | Functional | Saved list | Click Score → | 11-scoring.html?list=<id> | High | Playwright waitForURL | Pass | Opened 11-scoring.html?list=list-…
CT-29 | Save buttons disabled when no account passes | renderRun() | Functional | CSV with no recognisable header | Upload; view the list | Save list and Go to Scoring disabled | Medium | Playwright | Pass | Disabled
CT-30 | Script in file contents is shown as text, not run | esc() in every renderer | Non-functional · security | CSV with <img onerror> and <script> in name and company | Upload; view list and accounts | Text displayed literally; nothing runs | Critical | Playwright | Pass | No script executed
CT-31 | Download lead template | downloadTemplate() | Functional | — | Click "Download lead template (.csv)" | lead_template.csv with the 24 column names | Medium | Playwright waitForEvent("download") | Pass | lead_template.csv downloaded
CT-32 | Role switcher hides the page for roles without access | applyRoleToNav() | Functional + security | Role Viewer, then Sales rep | Switch role (demo) → Viewer; reload | Viewer sees "Not available for this role"; Sales rep sees the page | Medium | Playwright | Pass | As expected
CT-33 | Keyboard access: upload, tabs, filter pills | dropZone, .ftab, .seg-pill | Non-functional · accessibility | — | Tab through the page; try to upload without a mouse | Every control reachable and operable by keyboard | High | Playwright keyboard + axe-core | Fail | Drop zone not focusable (file input is display:none); tabs and filter pills are <div onclick>, not buttons

## Smoke
Smoke tests · A short, fast run over the critical path to decide whether a build is worth testing further. Stop at the first failure.
ID | Test case | Function / component under test | Aspect | Preconditions and test data | Steps | Expected result | Priority | How to automate | First run (3 Oct 2026) | Observed
SM-01 | Page opens without script errors | Page load | Functional | Network on | Open 10-prospecting.html | No console errors other than blocked fonts | Critical | Playwright console listener | Pass | Only font requests failed (blocked in the test)
SM-02 | Page title and heading | Page load | Functional | — | Read title and topbar | "Prospecting — DemandAI Pilot"; "Lead discovery and research" | High | Playwright | Pass
SM-03 | Page loads quickly | Page load | Non-functional · performance | — | Measure load | Under 2 s | High | Playwright | Pass | 162 ms (local file)
SM-04 | Excel library loads from the CDN | xlsx.full.min.js | Non-functional · availability | Real network | Check window.XLSX | Defined | Critical | Playwright | Not run | Served locally in this run
SM-05 | Upload zone, sample button and template button visible | renderStart() | Functional | — | Look | All three visible | Critical | Playwright | Pass
SM-06 | Sample data runs end to end | useSample() | Functional | Built-in sample | Click Use sample data | 6 issues · 9 of 12 accounts pass · 14 contacts in the list | Critical | Playwright | Pass | Exact match
SM-07 | Generated dataset uploads | onFile() | Functional | Lead_Research_Sample_Dataset.xlsx | Upload | Checks pop-up opens | Critical | Playwright | Pass
SM-08 | Correct sheet picked from the workbook | pickSheet() | Functional | Lead_Research_Sample_Dataset.xlsx | Read the sheet badge | "Lead template" | Critical | Playwright | Pass
SM-09 | All rows read | processLeads() | Functional | Lead_Research_Sample_Dataset.xlsx | Read "Rows read" | 7,498 | Critical | Playwright | Pass
SM-10 | Checks complete | openChecks() | Functional | Lead_Research_Sample_Dataset.xlsx | Wait for "View the list →" | Footer shows totals | Critical | Playwright | Pass | 6.4 s
SM-11 | Issues found on a dirty file | processLeads() | Functional | Lead_Research_Sample_Dataset.xlsx | Read Issues card | > 0, with stop / flag / info split | High | Playwright | Pass | 45 stop · 3,629 flag · 3,708 info
SM-12 | Final list opens | renderRun() | Functional | Lead_Research_Sample_Dataset.xlsx | Click View the list | Table with rows | Critical | Playwright | Pass | Slow: 7.3 s
SM-13 | Some accounts pass and some are excluded | buildAccounts() | Functional | Lead_Research_Sample_Dataset.xlsx | Read Accounts / Excluded cards | Both non-zero | High | Playwright | Pass | 1,168 pass · 275 excluded
SM-14 | Accounts tab opens | renderAccountsTab() | Functional | Lead_Research_Sample_Dataset.xlsx | Click Accounts | Table with 1,443 rows | High | Playwright | Pass
SM-15 | A filter works | Filter pills | Functional | Lead_Research_Sample_Dataset.xlsx | Click "In the final list" | 4,933 rows | High | Playwright | Pass
SM-16 | Search works | Search box | Functional | Lead_Research_Sample_Dataset.xlsx | Type a company name | Rows narrow to that company | High | Playwright | Pass
SM-17 | Select a contact | Checkbox | Functional | Lead_Research_Sample_Dataset.xlsx | Tick one row | Bar shows "1 prospect selected" | High | Playwright | Pass
SM-18 | Save a list (small) | saveList() | Functional | Sample data or 50 selected | Save | Toast "Saved as …" | Critical | Playwright | Pass
SM-19 | Save a list (full dataset) | saveList() | Functional | Lead_Research_Sample_Dataset.xlsx | Save list → Save | Saved | Critical | Playwright | Fail | Storage quota exceeded (see CT-26)
SM-20 | Saved list appears and survives a reload | loadLists() | Non-functional · persistence | One saved list | Reload; open Saved lists | List still there | High | Playwright | Pass | Still listed after reload
SM-21 | Go to Scoring from a saved list | Score → | Functional | One saved list | Click Score → | 11-scoring.html opens with the list | Critical | Playwright | Pass
SM-22 | Template downloads | downloadTemplate() | Functional | — | Click | lead_template.csv | Medium | Playwright | Pass
SM-23 | Wrong file type refused | readFileToGrids() | Functional | bad.txt | Upload | Toast | High | Playwright | Pass
SM-24 | File with no header refused safely | readTable() | Functional | CSV without template headers | Upload | 1 stop issue; save disabled | High | Playwright | Pass
SM-25 | Role without access is blocked | applyRoleToNav() | Functional | Role Viewer | Reload | No-access screen | High | Playwright | Pass
SM-26 | Narrow screen does not scroll sideways | Layout | Non-functional · compatibility | 390 × 844 viewport | Open the upload screen | No horizontal page scroll | Medium | Playwright viewport | Pass | Upload screen only; result tables not checked
SM-27 | Other browsers | Whole page | Non-functional · compatibility | Firefox, Safari (WebKit) | Repeat SM-01 to SM-18 | Same results | Medium | Playwright projects | Not run

## UAT
UAT tests · Business scenarios from the Lead discovery and research flow (3.1–3.6), run by sales ops or the client with the generated dataset and its answer key.
ID | Test case | Function / component under test | Aspect | Preconditions and test data | Steps | Expected result | Priority | How to automate | First run (3 Oct 2026) | Observed
UAT-01 | Sales ops can upload the client's file and get a validation result in under a minute | 3.1 Upload and map | Non-functional · performance + Functional | Lead_Research_Sample_Dataset.xlsx | Upload the file as received | Result visible within 60 s, columns mapped automatically | Critical | Manual, timed | Pass | 6.4 s to the check summary, 13.7 s to the list
UAT-02 | Columns in any order and with stars or different case are mapped | 3.1 Upload and map | Functional | Template with shuffled, upper-case columns | Upload | No column issues | High | Manual | Pass | Covered by UT-04
UAT-03 | Every missing required field is reported with a plain fix | 3.2 Check | Functional + usability | Row key MF-* rows | Look up 10 MF rows in the list | Each row shows the problem, what happens and how to fix it | Critical | Manual sample of 10 rows | Pass | 100% of MF-* rows flagged
UAT-04 | Duplicates are merged so nobody is contacted twice | 3.2 Check | Functional | Row key DUP-EXACT, DUP-EMAIL-CASE, DUP-UPDATED | Search the duplicated names | One contact each; "Duplicate of row N" shown | Critical | Manual | Pass | 280 of 280 merged
UAT-05 | Likely duplicates the rules can't prove (alias emails, same name and company) are shown for review | 3.2 Check | Functional | Row key DUP-FUZZY | Search the names | Flagged as possible duplicates | High | Manual | Gap | 67 of 70 not flagged: the same person can be contacted twice
UAT-06 | One company written two ways is treated as one account | 3.2 Check | Functional | Account key name_variant_used | Open Accounts; search the company | One account | High | Manual | Gap | 43 extra accounts created (1,443 shown vs 1,400 real)
UAT-07 | Invalid emails are never used as a channel | 3.2 Check | Functional | Row key EM-* rows | Check "Reachable by" for those contacts | Email not listed as a channel | Critical | Manual | Fail | Double-dot, trailing-dot and mailto: addresses still count as usable email (see UT-11)
UAT-08 | Personal, role and mismatched-domain emails are flagged for review | 3.2 Check | Functional | Row key EM-PERSONAL, EM-ROLE, EM-DOMAIN-MISMATCH | Look at the Issues column | Flagged | High | Manual | Gap | Not flagged; gmail and info@ addresses are treated as valid work emails
UAT-09 | Out-of-region accounts are excluded and the reason is logged | 3.5 Knock-outs | Functional | Account key ICP-REGION | Accounts → Excluded | Each shows "Outside the pilot region (country)" | Critical | Manual | Pass
UAT-10 | In-region accounts with a country written differently are kept | 3.5 Knock-outs | Functional | Account key FMT-COUNTRY | Accounts → Excluded | Not excluded | Critical | Manual | Fail | SG, Viet Nam, Phillipines and similar are excluded as out of region
UAT-11 | Accounts managed by a separate team are excluded | 3.5 Knock-outs | Functional | Account key ICP-MANAGED | Accounts → Excluded | "Managed separately by Client" | Critical | Manual | Pass | 49 managed accounts: 41 excluded for this reason, 8 already excluded for region (that rule runs first)
UAT-12 | Opted-out contacts never reach the final list | 3.6 Suppression | Functional | Row key SUP-OPTOUT, SUP-OPTOUT-CONFLICT | Filter "In the final list"; search them | None present | Critical | Manual + automated check | Pass | 0 opted-out or unconfirmed contacts in the final list
UAT-13 | Contacts with no or unknown consent basis are not contactable | 3.6 Suppression | Functional | Row key MF-CONSENT, FMT-CONSENT | Filter "Not contactable" | All present with the reason | Critical | Manual | Pass
UAT-14 | Consent basis is recorded per contact | 3.6 Suppression | Functional | Lead_Research_Sample_Dataset.xlsx | Final list Consent column | Every contact shows its basis | High | Manual | Pass
UAT-15 | Each account gets a vertical, account type, confidence and one-line reason | 3.4 Classify | Functional | Lead_Research_Sample_Dataset.xlsx | Accounts tab | All four shown for every account | High | Manual | Pass
UAT-16 | The "needs review" pile is manageable | 3.4 Classify | Non-functional · usability | Lead_Research_Sample_Dataset.xlsx | Accounts → Needs review | A small share of accounts | Medium | Manual | Gap | 854 of 1,443 (59%); every out-of-ICP industry lands here until the AI classifier is connected
UAT-17 | Instrumentation and control engineers are recognised as the primary persona | 3.4 Classify | Functional | Titles from the dataset | Filter by title "Instrument Engineer" | Persona = Primary | High | Manual | Fail | Shown as "None" (see UT-20)
UAT-18 | Out-of-ICP industries and distributors end up below the fit floor in Scoring | 3.4 → Scoring | Functional | Account key ICP-INDUSTRY, ICP-DISTRIBUTOR | Save the list; score it | Below fit floor | High | Manual across pages | Not run | Blocked for the full file by CT-26
UAT-19 | Validation report can be sent back to the client | 3.2 Check ("the report goes back") | Functional | Lead_Research_Sample_Dataset.xlsx | Look for an export of issues | Download of every issue with row, field, problem and fix | Critical | Manual | Gap | No export on this page; issues can only be read on screen
UAT-20 | Every problem carries a data-quality code (D1–D6) | 3.3 Readiness gate | Functional | Lead_Research_Sample_Dataset.xlsx | Look at the Issues column | Code visible per issue | High | Manual | Gap | Codes exist in the engine but are not shown in the table
UAT-21 | Readiness gate: is the data sufficient to start measuring? | 3.3 Readiness gate | Functional | Lead_Research_Sample_Dataset.xlsx | Look for coverage, recency, contactability, baseline summary | A go / no-go readiness report | High | Manual | Gap | Not on this page (only the check list and counts)
UAT-22 | Nothing is changed silently | 3.2 Check | Functional | Rows with $ numbers, Yes/No, whitespace | Compare list values to the file | Original values shown; every reformat has an issue | High | Manual | Pass
UAT-23 | Rep can send a chosen subset to Scoring | Hand off | Functional | Lead_Research_Sample_Dataset.xlsx | Select 50 contacts → Send to Scoring | Scoring opens with those 50 | High | Manual | Pass | Saved as "… · 50 selected"; Scoring opens with the list id
UAT-24 | Manager can save the whole screened universe and hand it to Scoring | Hand off | Functional + capacity | Lead_Research_Sample_Dataset.xlsx | Save and go to Scoring | Scoring opens with all 1,168 accounts | Critical | Manual | Fail | Fails at save: list too large for browser storage (CT-26)
UAT-25 | Working through 7.5k rows is comfortable | Final list | Non-functional · performance / usability | Lead_Research_Sample_Dataset.xlsx | Search, filter, scroll for 5 minutes | No freezes over 1 s | High | Manual | Fail | Each keystroke freezes the page for 2.5 s or more; first render 7.3 s
UAT-26 | Screens are clear without training | Whole page | Non-functional · usability | New user | Think-aloud session: upload, find the problems, save | Completes without help | Medium | Moderated session | Not run
UAT-27 | Lead data stays in the browser during the PoC | Whole page | Non-functional · security / privacy | Lead_Research_Sample_Dataset.xlsx | Watch network traffic during upload and save | No request carries contact data | High | DevTools / Playwright request log | Not run | Code reads the file locally; to confirm with a request log
UAT-28 | A corrected file produces fewer issues | 3.2 Check | Functional | Lead_Research_Sample_Dataset.xlsx with 20 Row key rows fixed | Re-upload | Issue count drops by those rows | Medium | Manual | Not run
UAT-29 | Each role sees what it should | Roles | Functional + security | Admin, Sales manager, Sales rep, Viewer | Switch roles | Viewer blocked; reps see only their accounts | Medium | Manual | Gap | Viewer blocked; reps still see every rep's accounts (owner not used to filter)
UAT-30 | Sample data is clearly marked as sandbox | Sample data | Functional | Use sample data | Save; open Saved lists | Marked sandbox everywhere | Low | Manual | Not run